
***Chesapeake Conservation Corps***

## Work Plan Sample

**www.chesapeakebaytrust.org / 410-974-2941**

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Major Projects & Tasks | Priority Level | Metrics | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug |
| Create and deliver K-12 environmental education tour |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1. Research existing EE programs and tours | 3 | 10 programs researched | x | x | x |  |  |  |  |  |  |  |  |  |
| 2. Create and modify curriculum to fit new needs | 2 | 1 curriculum created |  | x | x | x |  |  |  |  |  |  |  |  |
| 3. Test pilot curriculum | 1 | 1 test school group |  |  |  |  | x |  |  |  |  |  |  |  |
| 4. Begin delivering new tour | 2 | Deliver 5 tours/wk |  |  |  |  |  | x | x | x | x | x | x | x |
| Water Quality Monitoring |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1. Assist with water monitoring (nontidal 1x month; tidal 1x month) | 1 |  | x | x | x |  |  |  |  | x | x | x | x |  |
| 1. Water quality data entry | 1 |  | x | x | x | x | x | x | x | x | x | x | x | x |
| 1. Assist with annual scorecard | 2 |  |  |  | x | x | x | x | x |  |  |  |  |  |
| 1. Help develop creek-level scorecards based on scorecard data | 2 |  |  |  | x | x | x | x | x |  |  |  |  |  |
| 1. Assist in setting up Riverwatcher training | 2 |  |  |  |  |  |  |  |  |  |  | x | x | x |
| Assist with leading K-12 Env Education Programs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1. Chesapeake Champions Prep | 2 |  |  |  |  | x | x | x |  |  |  | x | x | x |
| 1. Chesapeake Champions Implement | 1 |  | x | x | x |  |  |  | x | x | x |  |  |  |
| 1. Oyster Education Program Outreach for next year | 3 |  | x | x | x | x | x |  |  |  |  |  |  |  |
| 1. Oyster Education Program Prep | 2 |  |  |  |  | x | x | x |  |  |  |  |  |  |
| 1. Oyster Education Program Implement | 1 |  | x | x | x |  |  |  |  |  |  | x | x | x |
| Capstone Project Create rain garden on host campus |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1. Identify site, determine area to be treated | 1 | 0.25 acre site TBD |  |  |  |  |  | x |  |  |  |  |  |  |
| 2. Research rain garden design guidance | 2 | 1 design obtained |  |  |  |  |  | x | x |  |  |  |  |  |
| 3. Apply for grant funding | 1 | 1 grant applied for |  |  |  |  |  | x |  |  |  |  |  |  |
| 4. Identify plant species and develop planting plan | 2 | 1 plan developed |  |  |  |  |  |  | x | x |  |  |  |  |
| 5. Organize volunteer event to plant rain garden | 2 | 100 vols solicited |  |  |  |  |  |  |  | x |  |  |  |  |
| 6. Conduct volunteer rain garden planting event | 1 | 10 vols |  |  |  |  |  |  |  |  | x |  |  |  |
| 7. Maintenance | 2 | 90% plant survivor |  |  |  |  |  |  |  |  | x | x | x | x |
| 8. Outreach – interpretive signage created | 2 | 1 sign built |  |  |  |  |  |  |  |  |  | x |  |  |
| Corps Elements |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1. Corps Training Events | 1 |  |  | x |  |  | x |  | x |  | x | x | x |  |
| 2. Peer-to-Peer Visits | 1 |  |  |  | x |  |  | x |  | x |  | x |  | x |